## YLT
| Project Name | An Online Booking System for Tourism Businesses (YEAMA LEONE TOURS)
| Project Duration | 84
| Project Start Date | 2023-05-15
| Project End Date | 2023-08-07 |  |  | May | [16 empty] | June | [29 empty] | July | [30 empty] | August
| Scrolling Increment | 0 | time axis 2023-05-15 to 2023-09-26
No. | Tasks | Taks Duration | Start Date | End Date | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
1 | Chapter One: Introduction | 20 | 2023-05-15 | 2023-06-03 | bar: 2023-05-15 to 2023-06-03
1.2 | Background of the Study | 10 | 2023-05-15 | 2023-05-24 | bar: 2023-05-15 to 2023-05-24
1.3 | Statement of the Problem | 5 | 2023-05-25 | 2023-05-29 | bar: 2023-05-25 to 2023-05-29
1.4 | Aims and Objectives | 1 | 2023-05-26 | 2023-05-26 | bar: 2023-05-26
1.5 | Hypotheses | 3 | 2023-05-27 | 2023-05-27 | bar: 2023-05-27
1.6 | Significance of the Study | 7 | 2023-05-28 | 2023-06-03 | bar: 2023-05-28 to 2023-06-03
2 | Chapter Two: Problem Definition & Scope | 15 | 2023-06-04 | 2023-06-06 | bar: 2023-06-04 to 2023-06-06
2.1 | Background and context | 1 | 2023-06-04 | 2023-06-04 | bar: 2023-06-04
2.2 | Detailed description of the problem | 2 | 2023-06-05 | 2023-06-06 | bar: 2023-06-05 to 2023-06-06
2.3 | Definition of System Scope | 2 | 2023-06-05 | 2023-06-06 | bar: 2023-06-05 to 2023-06-06
3 | Chapter Three: Literature Review | 20 | 2023-06-01 | 2023-06-20 | bar: 2023-06-01 to 2023-06-20
3.1 | The available methodology options | 7 | 2023-06-01 | 2023-06-07 | bar: 2023-06-01 to 2023-06-07
3.2 | The approach selected | 7 | 2023-06-08 | 2023-06-14 | bar: 2023-06-08 to 2023-06-14
3.3 | Justification of the selected approach | 3 | 2023-06-15 | 2023-06-17 | bar: 2023-06-15 to 2023-06-17
3.4 | Review of literature on the subject matter | 3 | 2023-06-18 | 2023-06-20 | bar: 2023-06-18 to 2023-06-20
4 | Chapter Four: Analysis & Design | 20 | 2023-06-21 | 2023-07-10 | bar: 2023-06-21 to 2023-07-06
4.1 | Analysis of current system | 8 | 2023-06-21 | 2023-06-28 | bar: 2023-06-21 to 2023-06-28
4.2 | Design options and choices made | 8 | 2023-06-29 | 2023-07-06 | bar: 2023-06-29 to 2023-07-06
4.3 | Design of the proposed system | 5 | 2023-07-06 | 2023-07-10 | bar: 2023-07-06 to 2023-07-10
5 | Chapter Five: Result & Discussion | 15 | 2023-07-11 | 2023-07-25 | bar: 2023-07-11 to 2023-07-25
5.1 | Presentation of results | 11 | 2023-07-11 | 2023-07-21 | bar: 2023-07-11 to 2023-07-21
5.2 | Implementation requirements and issues to be addressed in deployment | 3 | 2023-07-21 | 2023-07-23 | bar: 2023-07-21 to 2023-07-23
5.3 | Mention Results from system testing | 3 | 2023-07-22 | 2023-07-24 | bar: 2023-07-22 to 2023-07-24
6 | Chapter Six: Summary, Conclusion & Recommendation | 14 | 2023-07-25 | 2023-08-07 | bar: 2023-07-25 to 2023-08-07
6.1 | Summary of achievements in relation to stated objectives | 1 | 2023-07-25 | 2023-07-25 | bar: 2023-07-25
6.2 | Limitations of the Study and constraints | 5 | 2023-07-26 | 2023-07-30 | bar: 2023-07-26 to 2023-07-30
6.3 | Conclusions | 3 | 2023-07-31 | 2023-08-02 | bar: 2023-07-31 to 2023-08-02
6.4 | Recommendations | 5 | 2023-08-03 | 2023-08-07 | bar: 2023-08-03 to 2023-08-07
7 | References | 7 | 2023-08-08 | 2023-08-14 | bar: 2023-08-08 to 2023-08-14
8 | Appendices | 7 | 2023-08-09 | 2023-08-15 | bar: 2023-08-09 to 2023-08-15
[140 empty] | X | X | X | X
[140 empty] | X | X | X | X
[140 empty] | X | X | X | X | X | X
[140 empty] | X | X | X | X

## Sheet1 (2)
| Project Name | An Online Booking System for Tourism Businesses
| Project Duration | 36
| Project Start Date | 2023-05-15
| Project End Date | 2023-06-20 |  |  | May | [16 empty] | June | [29 empty] | July
| Scrolling Increment | 0 | time axis 2023-05-15 to 2023-07-20
No. | Tasks | Taks Duration | Start Date | End Date | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
1 | Phase 1: Project Initiation | 6 | 2023-05-15 | 2023-05-20 | bar: 2023-05-15 to 2023-05-20
1.2 | Define Project Objectives and Scope | 1 | 2023-05-15 | 2023-05-15 | bar: 2023-05-15
1.3 | Identify Stakeholders | 1 | 2023-05-16 | 2023-05-16 | bar: 2023-05-16
1.4 | Conduct Feasibility Study | 1 | 2023-05-17 | 2023-05-17 | bar: 2023-05-17
1.5 | Secure Required Resources | 1 | 2023-05-18 | 2023-05-18 | bar: 2023-05-18
1.6 | Develop Project Plan | 2 | 2023-05-19 | 2023-05-20 | bar: 2023-05-19 to 2023-05-20
2 | Phase 2: Requirements Gathering | 5 | 2023-05-21 | 2023-05-23 | bar: 2023-05-21 to 2023-05-23
2.1 | Conduct Stakeholder Interviews | 1 | 2023-05-21 | 2023-05-21 | bar: 2023-05-21
2.2 | Document Functional and Non-Functional Requirements | 2 | 2023-05-22 | 2023-05-23 | bar: 2023-05-22 to 2023-05-23
2.3 | Identify Integration Points | 2 | 2023-05-22 | 2023-05-23 | bar: 2023-05-22 to 2023-05-23
3 | Phase 3: System Design | 8 | 2023-05-24 | 2023-05-31 | bar: 2023-05-24 to 2023-05-31
3.1 | Architectural Design | 3 | 2023-05-24 | 2023-05-26 | bar: 2023-05-24 to 2023-05-26
3.2 | User Interface Design | 2 | 2023-05-27 | 2023-05-28 | bar: 2023-05-27 to 2023-05-28
3.3 | Database Design | 2 | 2023-05-27 | 2023-05-28 | bar: 2023-05-27 to 2023-05-28
3.4 | Backend & Integration Design | 2 | 2023-05-29 | 2023-05-30 | bar: 2023-05-29 to 2023-05-30
4 | Phase 4: Development (Agile Methodology) | 9 | 2023-05-31 | 2023-06-08 | bar: 2023-05-31 to 2023-06-08
4.1 | Sprint Planning | 1 | 2023-05-31 | 2023-05-31 | bar: 2023-05-31
4.2 | Backend Development | 4 | 2023-06-01 | 2023-06-04 | bar: 2023-06-01 to 2023-06-04
4.3 | Frontend Development | 3 | 2023-06-04 | 2023-06-06 | bar: 2023-06-04 to 2023-06-06
4.4 | Database Development | 2 | 2023-06-06 | 2023-06-07 | bar: 2023-06-06 to 2023-06-07
4.5 | Agile Development Iterations | 2 | 2023-06-07 | 2023-06-08 | bar: 2023-06-07 to 2023-06-08
4.6 | Stakeholder Feedback | 1 | 2023-06-08 | 2023-06-08 | bar: 2023-06-08
5 | Phase 5: User Training and System Deployment | 4 | 2023-06-09 | 2023-06-12 | bar: 2023-06-09 to 2023-06-12
5.1 | User Training | 1 | 2023-06-09 | 2023-06-09 | bar: 2023-06-09
5.2 | System Deployment | 1 | 2023-06-09 | 2023-06-09 | bar: 2023-06-09
5.3 | Advertising and Promotion | 3 | 2023-06-10 | 2023-06-12 | bar: 2023-06-10 to 2023-06-12
6 | Phase 6: Evaluation and Maintenance | 8 | 2023-06-13 | 2023-06-20 | bar: 2023-06-13 to 2023-06-20
6.1 | System Evaluation | 1 | 2023-06-13 | 2023-06-13 | bar: 2023-06-13
6.2 | Maintenance and Support | 5 | 2023-06-14 | 2023-06-18 | bar: 2023-06-14 to 2023-06-18
6.3 | Conduct testing and debugging to ensure proper functionality | 2 | 2023-06-19 | 2023-06-20 | bar: 2023-06-19 to 2023-06-20